## Slide 1
ZYCUS
Project Portfolio Health Report
July 2026
The portfolio is in a critical state with both monitored projects currently flagged Red and at High Risk, demanding immediate executive attention. TREND_1: Both Outokumpu_S2P and UniSan_S2P are universally rated "High" risk, indicating systemic challenges in project execution and external dependencies across the portfolio. TREND_2: UniSan_S2P is experiencing significant schedule slippage (14.8% behind) with over 50% of tasks
2
RED
0
AMBER
0
GREEN
Prepared by: AI Project Health Agent | Confidential

## Slide 2
Executive Summary
Portfolio RAG Status Dashboard
Outokumpu S2P
[RED]
PM: N/A | Stage: Configuration and Build phase Progress: 71% | Score: 1.35/2.0 The Outokumpu_S2P project is at a high risk level despite being ahead on percentage completion. Critical client sign-off...
UniSan S2P
[RED]
PM: N/A | Stage: Training Phase I Progress: 44% | Score: 0.50/2.0 The UniSan_S2P project is currently Red, experiencing significant schedule slippage with a 14.8% gap between actual and ...

## Slide 3
Schedule & Delivery Trends
Patterns identified across all monitored projects this month
01
Both Outokumpu_S2P and UniSan_S2P are universally rated "High" risk, indicating systemic challenges in project execution and external dependencies across the portfolio. TREND_2: UniSan_S2P is experiencing significant schedule slippage (14.8% behind) with over 50% of tasks
02
UniSan_S2P is experiencing significant schedule slippage (14.8% behind) with over 50% of tasks
Project Score Comparison
Outokumpu S2P 1.35/2.0
UniSan S2P 0.50/2.0

## Slide 4
Emerging Risks & Blockers
Systemic risks requiring immediate leadership attention
Projects flagged At Risk = HIGH: Outokumpu_S2P, UniSan_S2P

## Slide 5
Project Deep-Dives
Latest status snapshot per project
Outokumpu S2P [Red]
PM: N/A Stage: Configuration and Build phase Progress: 71% (expected ~57%) Tasks: 255 done / 467 total Top Risk: Critical...
UniSan S2P [Red]
PM: N/A Stage: Training Phase I Progress: 44% (expected ~59%) Tasks: 133 done / 343 total Top Risk: Significant schedule delay: The project is 14.8% behind schedule,...

## Slide 6
Strategic Recommendations
Actions recommended for leadership this month

## Slide 7
Appendix: Weekly RAG Log
Complete record of all weekly health assessments
Date
Project
RAG
Score
% Done
At Risk
2026-07-08
Outokumpu S2P
Red
1.35
71%
High
2026-07-08
UniSan S2P
Red
0.50
44%
High
2026-07-09
Outokumpu S2P
Red
1.35
71%
High
2026-07-09
UniSan S2P
Red
0.50
44%
High
2026-07-10
Outokumpu S2P
Red
1.35
71%
High
2026-07-10
UniSan S2P
Red
0.50
44%
High